## Sheet1
User Story Name | Description | Acceptance Criteria | Validation | Task List | Story point(1 sp=8 hrs) | Estimated Time | Actual Time | Start Time | End Time | Task Status | Owner | Comment
Home Page | Login/SignUp/Help or Support | User must be able to see the login page and enter the username and password to login to application.If the user forgets the password, he/she can click on the Forget Password link and can set the new password. | If the user is not registered then a message will be prompted that the login is invalid. | 1.UI Creation of Login Page. 2.Create login method in Controller class. 3.Create login method in Service layer. 4.Create authenticate and login method in dao. 5.Craete test cases for user validations. | 1 | 8hrs |  |  |  |  | Aravind
SignUp/Login | SignUp as Customer | SignUp using vaious fields: Name, Email, Password, CustomerId, Phone | All the fields must be valid.Name will contain only alphabates and spaces.Email must contain a valid email.Contact number must be 10 digit number and must contain only numbers.Password must contain alphabates,numbers,and special characters. | 1.UI Creation of Register Page. 2.Create Register method in Controller class. 2.Create entity class for customer. 4.Create Register method in Service layer. 5.Create authenticate and register method in dao. 6.Craete test cases for user validations. | 1 | 8hrs |  |  |  |  | Aravind
| SignUp as Driver | SignUp using various fields: Name, Email, Password, DriverId, Phone, Address, DOB, VehicleNo. | All the fields must be valid.Name will contain only alphabates and spaces.Email must contain a valid email.Contact number must be 10 digit number and must contain only numbers.Password must contain alphabates,numbers,and special characters. | 1.UI Creation of Register Page. 2.Create entity class for Driver. 3.Create Register method in Controller class. 4.Create Register method in Service layer. 5.Create authenticate and register method in dao. 6.Craete test cases for user validations. | 2 | 16hrs
Customer | Login as Customer: can login with registered email and password | After login customer can book a cab by entering source and destination and after that it will show expected fare for the trip, and then customer can onfirm the cab |  | UI Creation of cab booking page. | 2 | 16hrs |  |  |  |  | Shivaji
Driver | Login as Driver: can login with registered email and password | Driver will see trip request from customer side, and can accept or reject the cab |  | Driver will see trip request from customer side, and can accept or reject the cab | 2 | 16 |  |  |  |  | Nandini
Admin | Verify Driver | After the registration of driver, admin will verify the driver details and then driver can further proceed |  |  | 3 | 24 |  |  |  |  | Vineeta
| Fare Calculation | After getting source and destination price calculator will calculate the fare and will show it to the customers
Cab Booking | Estimated time | It will show the time taken by the driver to reach to the customers |  |  | 2 | 16 |  |  |  |  | Vineeta
| Show nearby cabs | will show the nearby cabs in a particular distance range with driver and vehicle details
| Set the driver status | free/booked
Vehicle | Type of cab | Type of cabs available for the customes(XL, share, micro, mini) |  |  | 2 | 16 |  |  |  |  | Nandini
Help/Support | SignUp/Login | If users having issue in login or signUp |  |  | 3 | 24 |  |  |  |  | Shivaji
| Payment | Payment related issues
| FAQs | Question asked by the users